## Slide 1
PROGRAMME IDENTIFICATION
EVOLUTION & GROWTH: SUSTAINABILITY OF PPHSN
PPHSN faces friction in data sharing, funding sustainability, member engagement, and outbreak manual progress. Root causes: no data-sharing agreements and no dedicated funding. Mitigation underway — increased allied member involvement, core funding secured, and a strategic implementation plan in development.

## Slide 2
LESSONS LEARNED
PPHSN IS EVERYONE'S BUSINESS
The SPRP collaborative approach revealed that siloed ownership limits progress. When PHD teams actively engage with service arms they support, PPHSN outcomes improve.
SYSTEMIC INSIGHT
Increase collaborative work within PHD and allied members to advance PPHSN activities.
ACTIONABLE PIVOT
All PHD teams must take ownership of the service arms they serve or support. PPHSN is not a single-programme responsibility — it is a shared institutional priority.

## Slide 3
STRATEGIC OPPORTUNITIES
FOCUS AREA: STRENGTHENING PPHSN THROUGH SHARED OWNERSHIP
PHASE 1
Establish data-sharing agreements and orientation
PHASE 2
Develop SOPs and regular allied-member orientation
PHASE 3
Distribute framework and activate resource mobilization
These phases build the foundation for sustained collaboration and resource mobilization across PPHSN.
STRATEGIC BENEFITS
Improved data and information sharing across partners
Higher-quality reporting and communication
Deeper PHD team involvement in PPHSN
CORE PREREQUISITE
PPHSN is the Pacific's primary regional mechanism for health security. Whole-of-PHD support is essential.